## Slide 1
Extra Tropical Storm Surge I/O resolution upgrade
Project Status as of 03/25/2014
Issues/Risks
Issues:
Is a TIN needed if we are doing a transparent (to end user) upgrade to the model?
Risks:
Mitigation:
Finances
Scheduling
Project Information and Highlights
Leads: Arthur Taylor (MDL)
Scope:
SPA Bugzilla 108 – Move to vertical structure and reintroduce the error messages to avoid ‘silent failure on 1/27’
Replace the forcing used by the ETSS model from GFS GRIB-1 1 degree winds to GFS GRIB-2 0.5 degree GFS winds. --- See 3/10/2014 email about need to move to GRIB2
Replace the output of the ETSS model from a 5km NDFD CONUS grid to a 2.5km NDFD CONUS grid. Also replace the resolution of the Alaska grids.
Correct the Alaska mask file used to provide guidance in the south Bering Sea.
Expected Benefits:
Bug fixes (Diagnostics and better guidance for south Bering Sea)
Take advantage of more accurate wind guidance to create more accurate storm surge guidance for extra-tropical storms
Updates the resulting guidance to the resolution that the WFO’s are currently working on.
Associated Costs: MDL in house maintenance.
Funding Sources: NA
Management Attention Required | Potential Management Attention Needed | On Target
G
Y
v1.0 9/14//07
G
R
G
1
G
G
Milestone (NCEP) | Date | Status
Initial EE setup (NCO Support) | 4/22/2014 | 
MDL testing complete | 5/6/2014 | 
Code delivered to NCO | 5/6/2014 | 
Technical Information Notice Issued | N/A? | 
CCB approve parallel data feed | TBD | 
Parallel testing begun in NCO | TBD | 
Real-Time Evaluation Ends | TBD | 
IT testing begins | TBD | 
IT testing ends | TBD | 
Management Briefing | TBD | 
Implementation | FY14Q3 | 
Notes: 1
1