## Slide 1
1
Extra Tropical Storm Surge V2.1-Alaska
Project Status as of 6/30/2015
Issues/Risks
Finances
Scheduling
Project Information and Highlights
Lead: Arthur Taylor, Christina Belton, Huiqing Liu, MDL and Becky Cosgrove, NCO
Scope:
Alaska basin (EBBC) –
  Create a basin that covers both Bering Sea and Arctic AK
  Determine best wind drag coefficient to use for EBBC
  Create a basin that has over land information
Produce overland inundation guidance from surge and tide
  Generate CONUS 625m grids for “surge and tide” and tide only grids
Include modeled tidal forcing for all grids
  37 constituents from ADCIRC EC-2014 (East coast and Gulf of Mexico)
  13 constituents from OSU – TPXO Global Tidal model (West coast and Alaska)
Adjust SHEF products to use MLLW instead of MHHW for a vertical datum
Expected Benefits:
Correct the Bering Strait problem in Alaska guidance
Produce overland guidance based on surge and tides
Associated Costs: Federal FTE labor and Contract Support
Funding Sources: MDL Base and Alaska Region funding
Computational Resources:
Currently – 6 CPU for 38 min. (Model and Post-Processing)
Will use – 14 CPU for 37 min. (Model and Post-Processing)
v1.0 09/14//07
G
Issues:.
Risks:
Mitigation:
Milestone (NCEP) | Date | Status
Initial coordination with SPA team | 5/13/2015 5/21 | Complete
MDL testing complete | 6/12/2015 6/26 | Complete 6/30
Final Code Delivered to NCO | 6/12/2015 6/26 | Complete 6/30
Technical Information Notice Issued | 6/29/2015 | 
SPA begins prep work for 30 day test | 6/15/2015 6/29 | 
30-day evaluation begins | 7/13/2015 7/27 | 
30-day evaluation ends | 8/11/2015 8/25 | 
IT testing ends | 7/10/2015 8/25 | 
Management Briefing | 8/21/2015 9/4 | 
Operational Implementation | 8/25/2015 9/8 | 
Y
R
Potential Management Attention Needed
On Track
R
G
G
G
Management Attention Required | Potential Management Attention Needed | On Target
G
Y
R